# Use Case Point (UCP)

## 📌 Definition

# Source: AI Source: Provided by: [Data Path: Persons Table -> ID Column: 1, Name_En Column: Motasem Essam] -> From: [ChatGPT] on [8/24/2025]

Use Case Point (UCP) is a software estimation technique based on use cases.
 It estimates the size, effort, and cost of a software project by analyzing:

- Actors (who interacts with the system),

- Use Cases (functionalities/scenarios of the system), and

- Technical & Environmental Factors (complexity, team skills, tools, etc.).

It is similar in spirit to Function Point Analysis (FPA) but works best when a Use Case Model is available.

## 🗂️ Steps in UCP Estimation

### 1. Classify & Weigh Actors

# Source: AI Source: Provided by: [Data Path: Persons Table -> ID Column: 1, Name_En Column: Motasem Essam] -> From: [ChatGPT] on [8/24/2025]

Actors = anything outside the system interacting with it (user, another system, device).

- Simple Actor (API, another system using defined protocol) → 1 point

- Average Actor (interactive system via protocol like TCP/IP, database) → 2 points

- Complex Actor (person via UI or complex interface) → 3 points

👉 Add them up = Unadjusted Actor Weight (UAW)

### 2. Classify & Weigh Use Cases

# Source: AI Source: Provided by: [Data Path: Persons Table -> ID Column: 1, Name_En Column: Motasem Essam] -> From: [ChatGPT] on [8/24/2025]

Each use case is classified by the number of transactions/steps:

- Simple (≤ 3 transactions) → 5 points

- Average (4–7 transactions) → 10 points

- Complex (≥ 7 transactions) → 15 points

👉 Add them up = Unadjusted Use Case Weight (UUCW)

### 3. Calculate Unadjusted Use Case Points (UUCP)

# Source: AI Source: Provided by: [Data Path: Persons Table -> ID Column: 1, Name_En Column: Motasem Essam] -> From: [ChatGPT] on [8/24/2025]

UUCP=UAW+UUCWUUCP = UAW + UUCW

### 4. Apply Technical Complexity Factor (TCF)

# Source: AI Source: Provided by: [Data Path: Persons Table -> ID Column: 1, Name_En Column: Motasem Essam] -> From: [ChatGPT] on [8/24/2025]

There are ~13 factors (performance, security, reusability, etc.), each rated 0–5, with defined weights.

TCF=0.6+(0.01×Σ (Factor × Weight))TCF = 0.6 + (0.01 \times \text{Σ (Factor × Weight)})

### 5. Apply Environmental Factor (EF)

# Source: AI Source: Provided by: [Data Path: Persons Table -> ID Column: 1, Name_En Column: Motasem Essam] -> From: [ChatGPT] on [8/24/2025]

There are ~8 factors (team experience, motivation, stability, etc.), each rated 0–5, with defined weights.

EF=1.4+(−0.03×Σ (Factor × Weight))EF = 1.4 + (-0.03 \times \text{Σ (Factor × Weight)})

### 6. Final Use Case Points (UCP)

# Source: AI Source: Provided by: [Data Path: Persons Table -> ID Column: 1, Name_En Column: Motasem Essam] -> From: [ChatGPT] on [8/24/2025]

UCP=UUCP×TCF×EFUCP = UUCP \times TCF \times EF

### 7. Convert to Effort

# Source: AI Source: Provided by: [Data Path: Persons Table -> ID Column: 1, Name_En Column: Motasem Essam] -> From: [ChatGPT] on [8/24/2025]

Organizations usually maintain a productivity factor (PF) (e.g., 20 hours per UCP).

Effort (hours)=UCP×PF\text{Effort (hours)} = UCP \times PF

## 📊 Example

# Source: AI Source: Provided by: [Data Path: Persons Table -> ID Column: 1, Name_En Column: Motasem Essam] -> From: [ChatGPT] on [8/24/2025]

A library management system has:

- Actors:

  - 2 simple (APIs) = 2 × 1 = 2

  - 1 complex (Librarian via UI) = 1 × 3 = 3
 👉 UAW = 5

- Use Cases:

  - 2 simple (check book availability, login) = 2 × 5 = 10

  - 1 complex (borrow/return process with >7 steps) = 15
 👉 UUCW = 25

UUCP=5+25=30UUCP = 5 + 25 = 30

Suppose:

- TCF = 1.05

- EF = 0.90

UCP=30×1.05×0.90=28.35UCP = 30 \times 1.05 \times 0.90 = 28.35

If PF = 20 hours/UCP →

Effort=28.35×20=567 hoursEffort = 28.35 \times 20 = 567 \text{ hours}

## 🎯 Advantages

# Source: AI Source: Provided by: [Data Path: Persons Table -> ID Column: 1, Name_En Column: Motasem Essam] -> From: [ChatGPT] on [8/24/2025]

- Directly uses use cases, which are already created in requirements.

- Considers actors, system complexity, environment.

- Works well in object-oriented projects.

## ⚠️ Disadvantages

# Source: AI Source: Provided by: [Data Path: Persons Table -> ID Column: 1, Name_En Column: Motasem Essam] -> From: [ChatGPT] on [8/24/2025]

- Needs a detailed use case model.

- Complexity classification can be subjective.

- Less effective for non-OO or non-use-case-driven projects.

✅ Summary:
 Use Case Point (UCP) = (Actors + Use Cases) × Technical × Environmental × Productivity Factor → Effort estimation.